## Project Management Data
Excel Sample Data
Project Management Data
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress
Marketing | Market Research | Alice | 2024-01-01 | 13 | 2024-01-14 | 78%
Marketing | Content Creation | Bob | 2024-01-14 | 14 | 2024-01-28 | 100%
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | 2024-02-19 | 45%
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | 2024-03-14 | 0%
Product Dev | Prototype Development | Ethan | 2024-01-02 | 18 | 2024-01-20 | 100%
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | 2024-01-30 | 78%
Product Dev | User Interface Design | Gabriel | 2024-02-04 | 25 | 2024-02-29 | 0%
Customer Svc | Service Improvement | Hannah | 2024-02-01 | 22 | 2024-02-23 | 100%
Customer Svc | Ticket Resolution | Ian | 2024-02-24 | 25 | 2024-03-20 | 100%
Customer Svc | Customer Feedback | Julia | 2024-03-21 | 30 | 2024-04-20 | 0%
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | 2024-02-24 | 10%
Financial | Financial Reporting | Mark | 2024-02-13 | 21 | 2024-02-09 | 78%
Financial | Investment Planning | Mark | 2024-03-19 | 25 | 2024-04-13 | 100%
Research | Market Trends Analysis | Nathan | 2024-01-02 | 23 | 2024-01-25 | 50%
Research | Data Collection | Olivia | 2024-01-26 | 32 | 2024-02-27 | 0%
Research | Research Paper Writing | Peter | 2024-02-28 | 27 | 2024-03-26 | 0%
Development | Software Development | Quinn | 2024-01-02 | 36 | 2024-02-07 | 100%
Development | Feature Enhancement | Rachel | 2024-02-08 | 34 | 2024-03-13 | 0%
Development | Code Review | Sam | 2024-03-14 | 30 | 2024-04-13 | 0%
Production | Manufacturing | Tim | 2024-01-03 | 47 | 2024-02-19 | 30%
Production | Quality Control | Ursula | 2024-02-17 | 27 | 2024-03-15 | 0%
Production | Packaging Design | Victor | 2024-03-14 | 22 | 2024-04-05 | 0%
Sales | Lead Generation | Wendy | 2024-01-03 | 60 | 2024-03-03 | 70%
Sales | Client Meetings | Xavier | 2024-01-06 | 20 | 2024-01-26 | 78%
Sales | Contract Negotiation | Yvette | 2024-02-03 | 35 | 2024-03-09 | 0%
Support | Technical Support | Zoe | 2024-01-01 | 25 | 2024-01-26 | 100%
Support | Bug Fixes | Aaron | 2024-01-27 | 31 | 2024-02-27 | 100%
Support | Software Updates | Bella | 2024-03-02 | 22 | 2024-03-24 | 0%
Operations | Process Optimization | Calvin | 2024-01-03 | 30 | 2024-02-02 | 40%
Operations | Inventory Management | Diane | 2024-02-03 | 25 | 2024-02-28 | 0%
Operations | Facility Maintenance | Edward | 2024-02-29 | 20 | 2024-03-20 | 0%
Consulting | Strategic Planning | Fiona | 2024-01-02 | 35 | 2024-02-06 | 60%
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | 2024-03-05 | 0%
Consulting | Client Advisory | Helen | 2024-03-06 | 25 | 2024-03-31 | 0%
Training | Employee Training | Isaac | 2024-01-04 | 27 | 2024-01-31 | 80%
Training | Certification Programs | Jane | 2024-01-28 | 30 | 2024-02-27 | 0%
Training | Skill Development | Kyle | 2024-02-28 | 22 | 2024-03-21 | 0%
Events | Event Planning | Laura | 2024-01-03 | 25 | 2024-01-28 | 30%
Events | Conference Management | Mike | 2024-02-03 | 20 | 2024-02-23 | 0%
Events | Sponsorship Coordinatio | n Nancy | 2024-02-24 | 35 | 2024-03-30 | 0%
Logistics | Supply Chain Management | Oscar | 2024-01-03 | 25 | 2024-01-28 | 50%
Logistics | Transportation Planning | Patricia | 2024-01-29 | 30 | 2024-02-28 | 100%
Logistics | Inventory Optimization | Quentin | 2024-03-29 | 20 | 2024-04-18 | 0%
Engineering | Product Design | Rachel | 2024-01-02 | 25 | 2024-01-27 | 20%
Engineering | System Integration | Sam | 2024-02-02 | 22 | 2024-02-24 | 0%
Engineering | Prototype Testing | Tom | 2024-02-23 | 27 | 2024-03-21 | 0%
Security | Office security man | Alnout | 2024-03-17 | 35 | 2024-06-26 | 69%